APPENDIX C: PROJECT GUIDE CHART

| Activity | Jan 23/01/26 | Feb 02/02/26 | Mar 03/03/26 | Apr 20/04/26 | May 15/05/26 | Jun 15/06/26 | Jul 17/07/26 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Locality survey | ███ |  |  |  |  |  |  |
| Market survey | ███ | █ |  |  |  |  |  |
| Enterprise selection |  | ███ |  |  |  |  |  |
| Project proposal |  | ███ |  |  |  |  |  |
| Budget preparation |  | ███ |  |  |  |  |  |
| Procurement |  | █ | ███ |  |  |  |  |
| House construction |  | ███ | ███ |  |  |  |  |
| Installation of equipment |  |  | ███ |  |  |  |  |
| Stocking chicks |  |  | ███ |  |  |  |  |
| Brooding |  |  | ███ | █ |  |  |  |
| Feeding programme |  |  | █ | ███ | ███ | ███ | ███ |
| Vaccination |  |  | █ | ███ | ███ | ███ | █ |
| Cleaning and sanitation |  |  | █ | ███ | ███ | ███ | ███ |
| Record keeping |  |  | █ | ███ | ███ | ███ | ███ |
| Growth monitoring |  |  |  | ███ | ███ | ███ | ███ |
| Marketing |  |  |  |  | ███ | ███ | ███ |
| Financial analysis |  |  |  |  |  | ███ | ███ |
| Portfolio compilation |  |  |  |  |  | █ | ███ |

Key: █ = Period during which the activity was undertaken.