APPENDIX E: PROJECT LOGICAL FRAMEWORK

| Project Narrative | Performance Indicators | Means of Verification | Assumptions |
| --- | --- | --- | --- |
| Goal: Improve sustainable poultry production and student practical skills. | Increased poultry production and improved learner competence. | Project reports, assessment records. | Continued support from school administration. |
| Purpose: Establish a profitable indigenous broiler enterprise. | 60 chicks stocked, 51 birds successfully reared and marketed, 85% survival rate. | Production records, sales records, financial records. | Adequate markets and proper management. |
| Output 1: Climate-smart poultry house constructed. | One poultry house completed and operational. | Construction reports, photographs. | Construction materials available. |
| Output 2: Chicks successfully reared. | Healthy flock maintained throughout the production period. | Mortality register, vaccination records, weight records. | Good disease control measures. |
| Output 3: Records maintained. | Daily production, financial and health records completed. | Record books. | Students maintain accurate records. |
| Output 4: Poultry marketed successfully. | 51 birds sold at a profit. | Sales receipts and cashbook. | Stable market prices. |
| Activities: Locality survey, budgeting, construction, procurement, stocking, feeding, vaccination, record keeping, marketing and evaluation. | Activities completed according to the work plan. | Progress reports, photographs and meeting minutes. | Adequate funding and timely procurement. |